## Task Sheet
Team Leader
|  | Name | Working Hrs/day | Leaves
| Group Members | anju | 4 | 0
|  | aiswarya | 4 | 0
|  | vandhana | 4
| Project Start Date | 2013-05-01
| Project Estimated End Date | ??
| Project End Date | ??
| Total Time Taken(in hrs) | 36
South Indian Recipe
Sl No | Task | Description | Estimated Start Date | Start Date | End Date | Estimated Hours | Time Taken(in Hr) | Done By | Status | Reviewed By | Lags
1 | Functional Document | Functionality sepc document | 2013-05-08 | 2013-05-01 | 2013-05-02 | 5 | 5 | Aiswarya vandana Anju | Completed | ??
2 | Database design |  | 2013-05-01 | 2013-05-01 | 2013-05-03 | 6 | 6 | Aiswarya,Anju,Vandana | Completed | ??
3 | Database design Sql |  | 2013-05-06 | 2013-05-06 |  |  |  | Aiswarya,Anju,Vandana | Completed
4 | Stored procedure |  |  | 2013-05-06 | 2013-05-07 |  |  | Aiswarya,Anju,Vandana | Completed
5 | Masterpage designing
6 | Project framework Settings |  |  | 2013-05-07 |  |  |  |  | In Progress
Coding
Sl No | Page | Description | Estimated Start Date | Start Date | End Date | Estimated Hours | Time Taken(in Hr) | Done By | Status | Reviewed By | Lags
ADMIN MODULE
7 | Manage Food Category | Design |  | 2013-05-09 | 2013-05-10 | 0.5 | 1 | Anju | completed
|  | Coding |  |  |  | 4 | 4
|  | Unit Test |  |  |  | 0.5
8 | ManageSubcategory | Design |  | 2013-05-11 | 2013-05-11 |  | 1 | Vandana | completed
|  | Coding |  | 2013-05-11 | 2013-05-11 |  | 3 | Vandana | completed
|  | Unit Test | [5 empty] | Vandana | completed
9 | Manage Region | Design |  | 2013-05-09 | 2013-05-09 | 0.5 | 1 | Aiswarya | completed
|  | Coding |  | 2013-05-09 | 2013-05-10 | 4 | 4 | Aiswarya | completed
|  | Unit Test |  | 2013-05-10 | 2013-05-10 | 0.5 |  | Aiswarya | completed
10 | Area | Design |  | 2013-05-10 | 2013-05-11 |  | 1 | Anju | completed
|  | Coding |  | 2013-05-11 | 2013-05-11 |  | 4 | Anju | completed
|  | Unit Test |  | 2013-05-11 | 2013-05-11 |  |  | Anju | completed
11 | Location | Design |  | 2013-05-13 | 2013-05-13 |  | 1 | Aiswarya | completed
|  | Coding |  | 2013-05-13 | 2013-05-15 |  | 4 | Aiswarya | completed
|  | Unit Test |  | 2013-05-15 | 2013-05-15 |  |  | Aiswarya | completed
12 | Recipe | Design |  | 2013-05-15 | 2013-05-16 |  | 1 | Anju,Aiswarya,Vandana | Completed
|  | Coding |  | 2013-05-20 | 2013-05-23 |  |  | Anju,Aiswarya,Vandana | Completed
|  | Unit Test |  | 8441994 | 8441994 |  |  | Anju,Aiswarya,Vandana | completed
13 | Manage Unit | Design |  | 2013-05-13 | 2013-05-13 | 0.5 | 1 | Aiswarya | completed
|  | Coding |  | 2013-05-13 | 2013-05-13 | 4 | 2 | Aiswarya | completed
|  | Unit Test |  | 2013-05-13 | 2013-05-13 | 0.5 |  | Aiswarya | completed
14 | AdminLogin | Design |  |  |  |  | 1 | Anju
|  | Coding |  |  |  |  | 2 | Anju
Unit Test
15 | Manage User | Design |  | 2013-05-11 | 2013-05-11 | 0.5 | 1 | Vandana | completed
|  | Coding |  | 2013-05-11 | 2013-05-12 | 4 | 4 | Vandana | completed
|  | Unit Test |  |  |  | 0.5 |  | Vandana | completed
PREMIUM USER MODULE
15 | User Login | Design |  | 2013-05-27 | 2013-05-27 | 0.5 |  | Aiswarya | completed
|  | Coding |  | 2013-05-27 | 2013-05-27 | 4 |  | Aiswarya | completed
|  | Unit Test |  | 2013-05-27 | 2013-05-27 | 0.5 |  | Aiswarya | completed
16 | Manage Favourite | Design |  | 2013-05-30 | 2013-05-30 | 0.5
|  | Coding |  | 2013-05-30 | 2013-05-30 | 4 |  |  | Completed
|  | Unit Test |  | 2013-05-30 | 2013-05-30 | 0.5
PUBLIC USER MODULE
17 | User Registration | Design |  | 2013-05-31 | 2013-05-31 | 0.5 |  | Aiswarya | Completed
|  | Coding |  | 2013-05-31 | 2013-05-31 | 4 |  | Aiswarya | Completed
|  | Unit Test |  | 2013-05-31 | 2013-05-31 | 0.5 |  | Aiswarya | Completed
18 | Search Receipe | Design |  | 2013-05-23 | 2013-05-23 | 0.5 |  |  | completed
|  | Coding |  | 2013-05-23 | 2013-05-28 | 4 |  |  | completed
|  | Unit Test |  | 2013-05-28 | 2013-05-28 | 0.5 |  |  | completed
19 | Post Comment | Design |  | 2013-06-01 | 2013-06-01 | 0.5 |  |  | Completed
|  | Coding |  | 2013-06-01 | 2013-06-01 | 4 |  |  | Completed
|  | Unit Test |  | 2013-06-01 | 2013-06-01 | 0.5 |  |  | Completed
20 | Receipe Rating | Design |  | 2013-05-30 | 2013-05-30 | 0.5 |  |  | Completed
|  | Coding |  | 2013-05-30 | 2013-05-30 | 4 |  |  | Completed
|  | Unit Test |  | 2013-05-30 | 2013-05-30 | 0.5 |  |  | Completed
21 | About Us | Design |  | 2013-06-01 | 2013-06-01 | 1 |  | Vandana | Completed
|  | Coding |  | 2013-06-01 | 2013-06-01 | 1 |  | Vandana | Completed
|  | Unit Test |  | 2013-06-01 | 2013-06-01 | 1 |  | Vandana | Completed
22 | HomePage | Design |  | 2013-05-30 | 2013-05-30 | 2 |  | Aiswarya | Completed
|  | Coding |  | 2013-05-30 | 2013-05-30 | 2.5 |  | Aiswarya | Completed
|  | Unit Test |  | 2013-05-30 | 2013-05-30 | 0.5 |  | Aiswarya | Completed
Note on K44: leave on 14/5/2013 -Aiswarya Sangeeth